Absolutely, Abhishek. Here's your fully integrated execution checklist—now enhanced with all the nested subtasks, formatting standards, QA protocols, automation hooks, and strategic alignment tasks. This version is structured for clarity and ready to be ported into Notion, Trello, Excel, or any project management tool.

# ✅ BDE Launchpad Training System – Master Execution Checklist

Structure: Phase → Step → Document → Subtasks → Microtasks

## 🟩 Phase 1: Foundation Setup

### 🔹 Step 1: Create Project Folder Structure

Folder: BDE Launchpad Training System/
Subtasks:

- ☐ Create root folder

- ☐ Create 12 subfolders

  - ☐ 01_Master Blueprint/

  - ☐ 02_Curriculum & Daily Schedule/

  - ☐ 03_Outreach Kit/

  - ☐ 04_Learner Toolkit/

  - ☐ 05_Mentor SOPs/

  - ☐ 06_LMS Content/

  - ☐ 07_CRM Setup/

  - ☐ 08_Performance Dashboards/

  - ☐ 09_BookStack Wiki/

  - ☐ 10_Pilot Launch Assets/

  - ☐ 11_Orientation & Motivation/

  - ☐ 12_Final Deployment Plan/

- ☐ Create README file for folder purpose

- ☐ Define versioning rules (e.g. v1.0, Final)

- ☐ Set naming conventions for all files

## 🟨 Phase 2: Build Core Documents

### 🔹 Step 2: Strategic Blueprint

Folder: 01_Master Blueprint/
File: BDE Launchpad – Strategic Blueprint.docx
Subtasks:

- ☐ Executive Summary

- ☐ Goals & Outcomes

- ☐ Payout Model

- ☐ Tools & Platforms

- ☐ Deployment Roadmap

- ☐ Apply formatting standards (font, header, logo)

- ☐ Add footer with version/date

- ☐ Peer review for clarity

### 🔹 Step 3: Curriculum & Daily Schedule

Folder: 02_Curriculum & Daily Schedule/
Subtasks:

- ☐ 12-Week Curriculum.docx

  - ☐ Weekly themes

  - ☐ Learning objectives

  - ☐ Milestone KPIs

- ☐ Daily Schedule Template.docx

  - ☐ Time blocks (9 hrs/day)

  - ☐ Activity types

- ☐ Mindset & Motivation Calendar.docx

  - ☐ Daily prompts

  - ☐ Weekly rituals

  - ☐ Reflection checkpoints

- ☐ QA: Test with 3 pilot learners

- ☐ Upload to LMS for dry run

### 🔹 Step 4: Outreach Kit

Folder: 03_Outreach Kit/
Subtasks:

- ☐ Client Persona Brief.docx

  - ☐ Industry segments

  - ☐ Pain points

  - ☐ Buying triggers

- ☐ Outreach Templates.docx

  - ☐ LinkedIn

  - ☐ Instagram

  - ☐ Email

- ☐ CRM Logging Sheet.xlsx

  - ☐ Lead fields

  - ☐ Status dropdowns

- ☐ Pitch Script.docx

  - ☐ Opening lines

  - ☐ Objection handling

  - ☐ Closing CTA

- ☐ Mentor Review Checklist.docx

  - ☐ Pitch quality

  - ☐ CRM hygiene

  - ☐ Follow-up discipline

- ☐ QA: Simulate outreach with 5 mentors

- ☐ Link CRM sheet to Zoho

### 🔹 Step 5: Learner Toolkit

Folder: 04_Learner Toolkit/
Subtasks:

- ☐ Kaizen Journal Template.docx

  - ☐ Daily reflection

  - ☐ Weekly goal setting

- ☐ FAQ & Escalation Guide.docx

  - ☐ Common queries

  - ☐ Escalation flowchart

- ☐ Pitch Rubric.docx

  - ☐ Scoring criteria

  - ☐ Examples

- ☐ Self-Evaluation Checklist.docx

  - ☐ Outreach volume

  - ☐ Conversion rate

  - ☐ CRM updates

- ☐ QA: Test rubric scoring with 3 mentors

- ☐ Format for LMS upload

### 🔹 Step 6: Mentor SOPs

Folder: 05_Mentor SOPs/
Subtasks:

- ☐ Daily Mentor Checklist.docx

  - ☐ Morning sync

  - ☐ Midday review

  - ☐ End-of-day feedback

- ☐ Escalation Protocol.docx

  - ☐ Issue types

  - ☐ Resolution timelines

- ☐ Feedback Templates.docx

  - ☐ Positive reinforcement

  - ☐ Constructive critique

- ☐ AMA Scheduling Guide.docx

  - ☐ Weekly slots

  - ☐ Topic rotation

- ☐ QA: Run mentor simulation

- ☐ Upload to BookStack Wiki

## 🟦 Phase 3: Platform Setup

### 🔹 Step 7: LMS Content

Folder: 06_LMS Content/
Subtasks:

- ☐ Week 1 Module.docx

- ☐ Week 2 – Client Acquisition Module.docx

- ☐ Week 3–12 Modules.docx

- ☐ Quiz & Assignment Bank.xlsx

  - ☐ MCQs

  - ☐ Roleplays

  - ☐ Case studies

- ☐ QA: Test LMS flow

- ☐ Tag SCORM-ready files

- ☐ Assign mentor review

### 🔹 Step 8: CRM Setup

Folder: 07_CRM Setup/
Subtasks:

- ☐ Zoho CRM Lead Template.xlsx

- ☐ Follow-Up Tracker.xlsx

- ☐ Closure Status Sheet.xlsx

- ☐ CRM SOP.docx

  - ☐ Lead lifecycle

  - ☐ Data hygiene rules

- ☐ QA: Test lead entry

- ☐ Validate follow-up logic

- ☐ Set mentor access levels

### 🔹 Step 9: Performance Dashboards

Folder: 08_Performance Dashboards/
Subtasks:

- ☐ Metabase Schema.docx

  - ☐ Table relationships

  - ☐ Field definitions

- ☐ Dashboard Mockups.pptx

  - ☐ Mentor view

  - ☐ Learner view

- ☐ Metrics Definitions.docx

  - ☐ Outreach volume

  - ☐ Conversion rate

  - ☐ Retention score

- ☐ QA: Validate schema

- ☐ Link to live CRM data

- ☐ Review with ops team

### 🔹 Step 10: BookStack Wiki

Folder: 09_BookStack Wiki/
Subtasks:

- ☐ Wiki Structure Plan.docx

- ☐ Content Index.xlsx

- ☐ Upload Checklist.docx

  - ☐ Formatting rules

  - ☐ Tagging conventions

- ☐ QA: Test navigation

- ☐ Assign content owners

- ☐ Set access permissions

## 🟥 Phase 4: Launch & Deployment

### 🔹 Step 11: Pilot Launch Assets

Folder: 10_Pilot Launch Assets/
Subtasks:

- ☐ Pilot Batch Tracker.xlsx

- ☐ Mentor Assignment Sheet.xlsx

- ☐ Feedback Collection Form.docx

- ☐ Iteration Notes.docx

- ☐ QA: Run dry pilot

- ☐ Log feedback themes

- ☐ Update iteration notes

### 🔹 Step 12: Orientation & Motivation

Folder: 11_Orientation & Motivation/
Subtasks:

- ☐ Orientation Script.docx

- ☐ Eye-Opener Session Prompts.docx

- ☐ Motivational Story Templates.docx

- ☐ Leaderboard Format.xlsx

- ☐ QA: Run mock orientation

- ☐ Test leaderboard logic

- ☐ Add mentor storytelling guide

### 🔹 Step 13: Final Deployment Plan

Folder: 12_Final Deployment Plan/
Subtasks:

- ☐ Cohort Rollout Plan.xlsx

- ☐ Payout Tracker.xlsx

- ☐ Retention Strategy.docx

- ☐ Career Ladder Framework.docx

- ☐ QA: Validate payout logic

- ☐ Review retention triggers

- ☐ Draft Phase 2 scale-up

Would you like me to now convert this into a Notion-ready database, a Trello board structure, or a progress dashboard template? Or shall we resume building your Strategic Blueprint with the Goals & Outcomes section?