## Sheet2
Absolutely, Abhishek. Let’s turn your step-by-step build plan into a trackable execution checklist—organized by phase, with clear progress markers so you can monitor completion, delegate tasks, or automate reminders.
✅ BDE Launchpad Training System – Execution Checklist
📁 Folder: BDE Launchpad Training System/
🟩 Phase 1: Foundation Setup
Step | Task | Status
1.1 | Create main project folder | Done
1.2 | Create 12 subfolders as per structure | Done
1.3 | Set up naming conventions and versioning rules | ☐
🟨 Phase 2: Build Core Documents
Step | Document | Folder | Status
2.1 | Strategic Blueprint | 01_Master Blueprint/ | ☐
2.2 | 12-Week Curriculum | 02_Curriculum & Daily Schedule/ | ☐
2.3 | Daily Schedule Template | 02_Curriculum & Daily Schedule/ | ☐
2.4 | Mindset & Motivation Calendar | 02_Curriculum & Daily Schedule/ | ☐
2.5 | Client Persona Brief | 03_Outreach Kit/ | ☐
2.6 | Outreach Templates | 03_Outreach Kit/ | ☐
2.7 | CRM Logging Sheet | 03_Outreach Kit/ | ☐
2.8 | Pitch Script | 03_Outreach Kit/ | ☐
2.9 | Mentor Review Checklist | 03_Outreach Kit/ | ☐
2.1 | Kaizen Journal Template | 04_Learner Toolkit/ | ☐
2.11 | FAQ & Escalation Guide | 04_Learner Toolkit/ | ☐
2.12 | Pitch Rubric | 04_Learner Toolkit/ | ☐
2.13 | Self-Evaluation Checklist | 04_Learner Toolkit/ | ☐
2.14 | Daily Mentor Checklist | 05_Mentor SOPs/ | ☐
2.15 | Escalation Protocol | 05_Mentor SOPs/ | ☐
2.16 | Feedback Templates | 05_Mentor SOPs/ | ☐
2.17 | AMA Scheduling Guide | 05_Mentor SOPs/ | ☐
🟦 Phase 3: Platform Setup
Step | Document | Folder | Status
3.1 | Week 1 Module | 06_LMS Content/ | ☐
3.2 | Week 2 – Client Acquisition Module | 06_LMS Content/ | ☐
3.3 | Week 3–12 Modules | 06_LMS Content/ | ☐
3.4 | Quiz & Assignment Bank | 06_LMS Content/ | ☐
3.5 | Zoho CRM Lead Template | 07_CRM Setup/ | ☐
3.6 | Follow-Up Tracker | 07_CRM Setup/ | ☐
3.7 | Closure Status Sheet | 07_CRM Setup/ | ☐
3.8 | CRM SOP | 07_CRM Setup/ | ☐
3.9 | Metabase Schema | 08_Performance Dashboards/ | ☐
3.1 | Dashboard Mockups | 08_Performance Dashboards/ | ☐
3.11 | Metrics Definitions | 08_Performance Dashboards/ | ☐
3.12 | Wiki Structure Plan | 09_BookStack Wiki/ | ☐
3.13 | Content Index | 09_BookStack Wiki/ | ☐
3.14 | Upload Checklist | 09_BookStack Wiki/ | ☐
🟥 Phase 4: Launch & Deployment
Step | Document | Folder | Status
4.1 | Pilot Batch Tracker | 10_Pilot Launch Assets/ | ☐
4.2 | Mentor Assignment Sheet | 10_Pilot Launch Assets/ | ☐
4.3 | Feedback Collection Form | 10_Pilot Launch Assets/ | ☐
4.4 | Iteration Notes | 10_Pilot Launch Assets/ | ☐
4.5 | Orientation Script | 11_Orientation & Motivation/ | ☐
4.6 | Eye-Opener Session Prompts | 11_Orientation & Motivation/ | ☐
4.7 | Motivational Story Templates | 11_Orientation & Motivation/ | ☐
4.8 | Leaderboard Format | 11_Orientation & Motivation/ | ☐
4.9 | Cohort Rollout Plan | 12_Final Deployment Plan/ | ☐
4.1 | Payout Tracker | 12_Final Deployment Plan/ | ☐
4.11 | Retention Strategy | 12_Final Deployment Plan/ | ☐
4.12 | Career Ladder Framework | 12_Final Deployment Plan/ | ☐
🧭 Tracking Tips
✅ = Completed
☐ = Pending
🟡 = In Progress
🔁 = Needs Revision
You can use this checklist in Notion, Excel, Trello, or even BookStack to track progress across teams. Want me to help you set this up in one of those platforms next? Or shall we now begin drafting the Goals & Outcomes section of your Strategic Blueprint?

## Sheet1
BDE Launchpad Training System - Master Build Checklist
Phase | Task ID | Task Description | Folder / Location | Deliverable | Status | Priority | Notes
1. Foundation | F-01 | Define Project Goals, Outcomes & Payout Model | 01_Master_Blueprint | Strategic_Blueprint.docx | ⬜ | High | Include exec summary, tools, roadmap.
| F-02 | Create Project Folder Structure | Root Directory | Folder Tree | ✅ | High | Already completed.
2. Curriculum | C-01 | Design 12-Week Curriculum Outline | 02_Curriculum | 12-Week_Curriculum_Map.docx | ⬜ | High | Weekly themes, deliverables, outcomes.
| C-02 | Build Detailed Daily Schedule (9 hrs) | 02_Curriculum | Daily_Schedule_Template.xlsx | ⬜ | High | Blocks for mindset, outreach, CRM, etc.
| C-03 | Create Mindset & Motivation Calendar | 02_Curriculum | Mindset_Calendar.docx | ⬜ | Medium | Weekly themes + daily story prompts.
3. Outreach Engine | O-01 | Write 10+ Outreach Templates | 03_Outreach_Kit | Templates_Library.docx | ⬜ | High | LinkedIn, Instagram, Email variants.
| O-02 | Define 3 Core Client Personas | 03_Outreach_Kit | Client_Personas.pdf | ⬜ | High | Freelancers, solopreneurs, agencies.
| O-03 | Create Simple CRM Logging Sheet | 03_Outreach_Kit | CRM_Log_Sheet.xlsx | ⬜ | High | Lead name, platform, status, follow-up.
| O-04 | Draft the Core Pitch Script | 03_Outreach_Kit | Pitch_Script_Master.docx | ⬜ | High | Hook, problem, solution, CTA.
| O-05 | Build Mentor Outreach Review Checklist | 03_Outreach_Kit | Mentor_Review_Checklist.docx | ⬜ | Medium | Clarity, ethics, personalization checks.
4. Learner Toolkit | L-01 | Design Kaizen Daily Journal Template | 04_Learner_Toolkit | Kaizen_Journal_Template.docx | ⬜ | Medium | Daily reflections, habit tracking.
| L-02 | Write FAQ & Escalation Guide | 04_Learner_Toolkit | FAQ_Guide.docx | ⬜ | Medium | Support channels, how to get help.
| L-03 | Build Peer Pitch Rubric | 04_Learner_Toolkit | Pitch_Rubric.docx | ⬜ | Low | Scoring format for peer reviews.
| L-04 | Create Self-Evaluation Checklist | 04_Learner_Toolkit | Self_Evaluation_Checklist.docx | ⬜ | Low | Confidence, ethics, CRM hygiene.
5. Mentor Hub | M-01 | Write Daily Mentor SOP Checklist | 05_Mentor_SOPs | Daily_Mentor_Checklist.docx | ⬜ | High | Attendance, CRM review, feedback.
| M-02 | Define Learner Escalation Protocol | 05_Mentor_SOPs | Escalation_Protocol.docx | ⬜ | High | For behavior, ethics, performance issues.
| M-03 | Create Feedback Templates | 05_Mentor_SOPs | Feedback_Templates.docx | ⬜ | Medium | Weekly reviews, pitch scoring.
| M-04 | Build AMA Session Scheduling Guide | 05_Mentor_SOPs | AMA_Scheduling_Guide.docx | ⬜ | Low | Weekly Q&A, motivation sessions.
6. LMS Setup | LMS-01 | Build & Upload Week 1-2 Modules | 06_LMS_Content | Week_1-2_Modules.zip | ⬜ | High | Lectures, assignments, quizzes.
| LMS-02 | Build & Upload Week 3-12 Modules | 06_LMS_Content | Week_3-12_Modules.zip | ⬜ | High | Drip content enabled.
| LMS-03 | Create Quiz & Assignment Bank | 06_LMS_Content | Quiz_Bank.xlsx | ⬜ | Medium | Questions and answers for all weeks.
7. CRM Setup | CRM-01 | Design Zoho CRM Lead Template | 07_CRM_Setup | Zoho_Lead_Template.xlsx | ⬜ | High | Fields for outreach tracking.
| CRM-02 | Build Follow-Up Sequence Tracker | 07_CRM_Setup | Follow_Up_Tracker.xlsx | ⬜ | High | Track status and next steps.
| CRM-03 | Define Deal Closure Sheet | 07_CRM_Setup | Closure_Status_Sheet.xlsx | ⬜ | High | Demo scheduled, won, lost.
| CRM-04 | Write CRM Hygiene SOP | 07_CRM_Setup | CRM_SOP.docx | ⬜ | Medium | Mentor review flow and rules.
8. Dashboards | D-01 | Design Metabase Data Schema | 08_Performance_Dashboards | Metabase_Schema.docx | ⬜ | Medium | Map data points for outreach, payout.
| D-02 | Create Dashboard Mockups | 08_Performance_Dashboards | Dashboard_Mockups.pptx | ⬜ | Low | Visual layout for each dashboard.
| D-03 | Define Key Metrics & KPIs | 08_Performance_Dashboards | KPI_Definitions.docx | ⬜ | Medium | Formal definitions and thresholds.
9. Knowledge Wiki | W-01 | Plan BookStack Wiki Structure | 09_BookStack_Wiki | Wiki_Structure_Plan.docx | ⬜ | Low | Page hierarchy and categories.
| W-02 | Create Content Index | 09_BookStack_Wiki | Content_Index.xlsx | ⬜ | Low | Checklist of all pages to create.
| W-03 | Write Final Upload Checklist | 09_BookStack_Wiki | Wiki_Upload_Checklist.docx | ⬜ | Low | Sync guide for LMS + Wiki.
10. Pilot Launch | P-01 | Create Pilot Batch Tracker | 10_Pilot_Launch | Pilot_Tracker.xlsx | ⬜ | High | Track 50-100 learners.
| P-02 | Assign Mentors to Cohorts | 10_Pilot_Launch | Mentor_Assignments.xlsx | ⬜ | High | Map mentors to learners.
| P-03 | Build Feedback Collection Form | 10_Pilot_Launch | Feedback_Form.docx | ⬜ | Medium | For Kaizen journals & mentor reviews.
| P-04 | Create Iteration Log | 10_Pilot_Launch | Iteration_Notes.docx | ⬜ | Medium | Document improvements for V2.
11. Orientation | OR-01 | Write Day 1 Orientation Script | 11_Orientation_Motivation | Orientation_Script.docx | ⬜ | High | Welcome, rules, expectations.
| OR-02 | Create "Eye-Opener" Session Prompts | 11_Orientation_Motivation | Eye_Opener_Prompts.docx | ⬜ | Medium | Salary myths, global habits.
| OR-03 | Build Motivational Story Templates | 11_Orientation_Motivation | Story_Templates.docx | ⬜ | Low | Bamboo, river, ladder analogies.
| OR-04 | Design Leaderboard Format | 11_Orientation_Motivation | Leaderboard_Template.xlsx | ⬜ | Low | For weekly shoutouts.
12. Deployment | DEP-01 | Finalize Cohort Rollout Plan | 12_Final_Deployment | Cohort_Rollout_Plan.xlsx | ⬜ | High | Schedule for 100 cohorts.
| DEP-02 | Create Master Payout Tracker | 12_Final_Deployment | Payout_Tracker.xlsx | ⬜ | High | Calculate monthly + bonus payouts.
| DEP-03 | Write Retention Strategy Doc | 12_Final_Deployment | Retention_Strategy.docx | ⬜ | Medium | Plan for keeping top performers.
| DEP-04 | Build Career Ladder Framework | 12_Final_Deployment | Career_Ladder.docx | ⬜ | Medium | Growth path to Team Lead, Manager.
Status Key: