To give someone a comparatory video Honeywell Jijaji Great move, Abhishek. Let’s break down the entire BDE Launchpad build into a realistic 8-hour/day task structure, so you can see exactly how long it’ll take to launch properly—without burning out or losing clarity.

# 🕒 Project Timeline: BDE Launchpad System

Workload: 8 hours/day · 6 days/week
Total Duration to Launch: 4 weeks (24 working days)
Goal: Fully deploy LMS, CRM, dashboards, mentor systems, and outreach kits for pilot launch

## 📅 Week 1 – Strategy, Curriculum & Toolkit (6 days)

| Day | Focus Area | Tasks (8 hrs/day) |
| --- | --- | --- |
| 1 | Strategic Blueprint | Finalize goals, payout model, learner persona |
| 2 | Curriculum Design | Build 12-week structure + daily schedule |
| 3 | Outreach Kit Creation | Write templates, pitch scripts, CRM sheet |
| 4 | Learner Toolkit | Kaizen journal, FAQ, rubrics, SOPs |
| 5 | Mentor SOPs | Daily checklist, escalation flow, feedback forms |
| 6 | Master Document Compilation | Format everything into Word, add TOC + polish |

✅ Deliverables: Master blueprint, outreach kit, learner & mentor toolkits

## 📅 Week 2 – Platform Setup (6 days)

| Day | Focus Area | Tasks |
| --- | --- | --- |
| 7 | LMS Setup (Open edX) | Create course shell, upload Week 1–2 modules |
| 8 | LMS Configuration | Enable quizzes, peer reviews, drip content |
| 9 | CRM Setup (Zoho Sandbox) | Create lead templates, follow-up tracker |
| 10 | Teams Setup | Create cohort channels, mentor groups |
| 11 | BookStack Wiki | Upload toolkits, SOPs, rubrics, FAQs |
| 12 | Metabase Dashboard Design | Define schema, mock up outreach & payout views |

✅ Deliverables: LMS live, CRM sandbox ready, Teams channels active, BookStack hosted, dashboard schema defined

## 📅 Week 3 – Content Upload & Testing (6 days)

| Day | Focus Area | Tasks |
| --- | --- | --- |
| 13 | Upload Week 3–6 Modules | LMS content, quizzes, assignments |
| 14 | Outreach Simulation | Test CRM logging, pitch review flow |
| 15 | Dashboard Integration | Connect LMS + CRM data to Metabase |
| 16 | Mentor Training | SOP walkthrough, feedback simulation |
| 17 | Learner Onboarding Prep | Welcome kit, orientation script, motivation rituals |
| 18 | Pilot Batch Selection | Choose 50–100 learners, assign mentors |

✅ Deliverables: Mid-course content uploaded, systems tested, pilot batch ready

## 📅 Week 4 – Pilot Launch & Monitoring (6 days)

| Day | Focus Area | Tasks |
| --- | --- | --- |
| 19 | Orientation Broadcast | YouTube Live + Teams AMA |
| 20 | Week 1 Execution | Monitor LMS usage, mentor feedback |
| 21 | Week 2 Outreach Monitoring | Track CRM entries, pitch quality, closures |
| 22 | Dashboard Review | Analyze outreach volume, payout eligibility |
| 23 | Feedback Collection | Kaizen logs, mentor reviews, learner surveys |
| 24 | Iteration & Final Prep | Refine scripts, payout logic, finalize full rollout plan |

✅ Deliverables: Pilot launched, performance tracked, feedback loop active

## 🧮 Total Time to Launch:

24 working days = 4 weeks (at 8 hours/day, 6 days/week)
You’ll have a fully operational, scalable training system ready for deployment—with real client closures by Week 2 and payout tracking by Week 4.

If you’d like, I can now help you:

- Create a printable Gantt chart-style timeline

- Build a daily task checklist for Week 1

- Or prep your orientation script for Day 19’s broadcast

Let’s keep this momentum sharp and focused.

Perfect, Abhishek. Let’s start from absolute zero and build your BDE Launchpad Training System from scratch—with a clear folder structure so you can organize every document, template, and asset as you go.

# 🧱 Step-by-Step Build Plan (From Scratch)

## 🟩 Phase 1: Foundation Setup

### ✅ Step 1: Create Your Project Folder

Name it: BDE Launchpad Training System

Inside this, create the following subfolders:

BDE Launchpad Training System/

├── 01_Master Blueprint/

├── 02_Curriculum & Daily Schedule/

├── 03_Outreach Kit/

├── 04_Learner Toolkit/

├── 05_Mentor SOPs/

├── 06_LMS Content/

├── 07_CRM Setup/

├── 08_Performance Dashboards/

├── 09_BookStack Wiki/

├── 10_Pilot Launch Assets/

├── 11_Orientation & Motivation/

├── 12_Final Deployment Plan/

## 🟨 Phase 2: Build Core Documents

### ✅ Step 2: Master Blueprint (01_Master Blueprint/)

Create a Word doc titled: BDE Launchpad – Strategic Blueprint.docx
Include:

- Executive summary

- Goals & outcomes

- Payout model

- Tools & platforms

- Deployment roadmap

### ✅ Step 3: Curriculum & Schedule (02_Curriculum & Daily Schedule/)

Create:

- 12-Week Curriculum.docx

- Daily Schedule Template.docx (9 hrs/day × 6 days/week)

- Mindset & Motivation Calendar.docx

### ✅ Step 4: Outreach Kit (03_Outreach Kit/)

Create:

- Client Persona Brief.docx

- Outreach Templates.docx (LinkedIn, Instagram, Email)

- CRM Logging Sheet.xlsx

- Pitch Script.docx

- Mentor Review Checklist.docx

### ✅ Step 5: Learner Toolkit (04_Learner Toolkit/)

Create:

- Kaizen Journal Template.docx

- FAQ & Escalation Guide.docx

- Pitch Rubric.docx

- Self-Evaluation Checklist.docx

### ✅ Step 6: Mentor SOPs (05_Mentor SOPs/)

Create:

- Daily Mentor Checklist.docx

- Escalation Protocol.docx

- Feedback Templates.docx

- AMA Scheduling Guide.docx

## 🟦 Phase 3: Platform Setup

### ✅ Step 7: LMS Content (06_LMS Content/)

Create:

- Week 1 Module.docx

- Week 2 – Client Acquisition Module.docx

- Week 3–12 Modules.docx

- Quiz & Assignment Bank.xlsx

### ✅ Step 8: CRM Setup (07_CRM Setup/)

Create:

- Zoho CRM Lead Template.xlsx

- Follow-Up Tracker.xlsx

- Closure Status Sheet.xlsx

- CRM SOP.docx

### ✅ Step 9: Performance Dashboards (08_Performance Dashboards/)

Create:

- Metabase Schema.docx

- Dashboard Mockups.pptx

- Metrics Definitions.docx

### ✅ Step 10: BookStack Wiki (09_BookStack Wiki/)

Create:

- Wiki Structure Plan.docx

- Content Index.xlsx

- Upload Checklist.docx

## 🟥 Phase 4: Launch & Deployment

### ✅ Step 11: Pilot Launch Assets (10_Pilot Launch Assets/)

Create:

- Pilot Batch Tracker.xlsx

- Mentor Assignment Sheet.xlsx

- Feedback Collection Form.docx

- Iteration Notes.docx

### ✅ Step 12: Orientation & Motivation (11_Orientation & Motivation/)

Create:

- Orientation Script.docx

- Eye-Opener Session Prompts.docx

- Motivational Story Templates.docx

- Leaderboard Format.xlsx

### ✅ Step 13: Final Deployment Plan (12_Final Deployment Plan/)

Create:

- Cohort Rollout Plan.xlsx

- Payout Tracker.xlsx

- Retention Strategy.docx

- Career Ladder Framework.docx

## 🧠 How Long Will This Take?

With an 8-hour/day schedule, here’s your realistic timeline:

| Phase | Duration |
| --- | --- |
| Foundation & Blueprint | 3 days |
| Curriculum & Toolkits | 4 days |
| LMS + CRM + Dashboards | 6 days |
| Wiki + SOPs + Orientation | 4 days |
| Pilot Launch Prep | 4 days |
| Final Deployment Plan | 3 days |

Total: 24 working days → 4 weeks

Would you like me to now start building the first document:
BDE Launchpad – Strategic Blueprint.docx section by section? I’ll make it Word-ready and structured for clarity.